## Sheet1
Status | CVT WFT Changes requried | CVT WFT functions | RP Comments
Not possible as some times if date will also move forward if time goes after 12 midnight after reducing the time | To capture UK time default i.e. IST - 4.5 hrs |  | To check (RP to confirm by 17th Aug)
Not Possible as the whole table needs to be checked during inserting and updating the record | Duplication addition not allowed for CVT New Request Activity Type | Match with Org ID and have a pop up for duplicate addition (basis the Activity Type) | Possible
Done | Org ID mandatory for Activity Types CVT New Request, Reactivation and Org Creation | Minimum 5 characters | Possible
Done | DUNS Mandatory when the org status is changed to Pending SPOE (Activity Types: CVT New Request and Reactivation) | Minimum 5 characters | Possible
Done | Duplication check between DUNS and Org ID | Both values should not be same | Possible
Done | Columns: KYC Completed Date and First Check completed date can be removed as it has no significance and is not captured/measured anywhere |  | Possible
Done | Query Sent Date should be greater than Received Date as applicable | Have a pop up if it is less or equal | Possible
Done | Query Resolved Date to be greater than Query Sent Date and Received Date | Have a pop up if it is less or equal | Possible
Not possible | Role wise pop up if the Query Sent Date/Approved Date is more than 24 hrs/96 hrs (as applicable) as an alarm for TAT Miss case (for Activity Type : CVT New Request) | TAT Alert | To check (RP to confirm by 17th Aug)
Not possible | Capture the BU details from the Email ID of requestor automatically from outlook |  | Conditionally possible | BU Names are already used in the current MI Reports and change in approach would change the teminology of the BU
Done | Legal Entity column to be added for CVT New Request Activity Type |  | Possible (SP to provide drop downs)
Not possible | Can the DOTNET workflow be linked to the CVT inflow directly? So all initial entry required will be updated, whoever picks the record has to update his own name against the record and proceed |  | To check (Lot of R&D required will take time)
Done | Requestor's Email Id requestors location and segment should be captured automatically from outlook |  | Possible (with the exact drop down)
Not done. Need more clarification as the new names are not clear | Revised Query Categories | Change the current Query categories | SP to send revised list
Done | Separate dropdown for Activity Types: Org Creation, Adhoc Project, BAU Project